## Phase 1
Phase 1 | Identify Test Environment |  | Collect Details From
Business / Business Analyst
| Application | JPetStore | Functional Testing / Automation Testing
| URL | https://jpetstore.aspectran.com/

## Phase 2
Phase 2 | Identify Performance Metrics |  |  | Collect From
Business / Business Analyst
Service Level Agreement (SLA)
| Response Time | Min | <0.5
|  | Avg | <1.0
|  | Max | <2.0
|  | 90th Percentile | <1.5
|  | 95th Percentile | <1.8
| Hits/Sec | ThroughPut

## Phase 3
Phase 3 | Plan and Design Performance Test |  | Collect From
Business / Business Analyst
In Scope |  |  |  | 300 |  | Complexity | Efforts in Days |  |  | Out Scope
Web Application | Scenario 1 | Shopping Fish | Login Details | 10 | 30 | Medium | 2 | Create the script |  | Security Testing
Web Application | Scenario 2 | Shopping Dog | Login Details | 10 | 30 | Medium | 2 | Parameterize |  | Functional Testing
Web Application | Scenario 3 | Shopping Reptiles | Login Details | 5 | 15 | Medium | 2 | Correlate |  | AUT | User Acceptance Testing
Web Application | Scenario 4 | Shopping Cats | Login Details | 5 | 15 | Medium | 2 | Set the transaction |  | OAT | Operational Acceptance Testing
Web Application | Scenario 5 | Shopping Birds | Login Details | 5 | 15 | Medium | 2 | Inserting Think Time
Web Application | Scenario 6 | Login & Logout | Login Details | 5 | 15 | Medium | 2 | Pacing
Web Application | Scenario 7 | Add to cart | Login Details | 40 | 120 | Medium | 2 | Iteration
API Call | Scenario 8 | Search |  | 20 | 60 | Medium | 2
16
|  |  |  | 100 | 300 | Numbers of Testers = 2 | 8
[7 empty] | 25% | Last minute changes
| Web Application | [5 empty] | 2 | Application Stable
| Scenario 1 | Shopping Fish |  |  |  |  | 10 | Functional testing team
Automation testing team
| Step # | Transaction Names | Test Data Required |  | Assertion |  | Test data | Dev
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps |  |  | Functional testing team
| Step 1 | Click on JPetStore Demo |  |  | Fish |  |  | Performance testing team
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Fish |  |  | Angelfish
| Step 5 | Click on Product | Item is FI-SW-01 |  | FI-SW-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Proceed to Checkout | Atleast one item added to cart |  | Payment Details
| Step 8 | Enter Payment details and continue | Payment Card Data & Address |  | Please confirm the information below and then press continue.
| Step 9 | Click on Confirm |  |  | Thank you, your order has been submitted.
| Step 10 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 2 | Shopping Dog
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Dog
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Dog |  |  | Bulldog
| Step 5 | Click on Product | Item is K9-BD-01 |  | K9-BD-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Proceed to Checkout | Atleast one item added to cart |  | Payment Details
| Step 8 | Enter Payment details and continue | Payment Card Data & Address |  | Please confirm the information below and then press continue.
| Step 9 | Click on Confirm |  |  | Thank you, your order has been submitted.
| Step 10 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 3 | Shopping Reptiles
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Dog
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Reptiles |  |  | Rattlesnake
| Step 5 | Click on Product | Item is RP-SN-01 |  | RP-SN-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Proceed to Checkout | Atleast one item added to cart |  | Payment Details
| Step 8 | Enter Payment details and continue | Payment Card Data & Address |  | Please confirm the information below and then press continue.
| Step 9 | Click on Confirm |  |  | Thank you, your order has been submitted.
| Step 10 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 4 | Shopping Cats
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Cat
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Cats |  |  | Manx
| Step 5 | Click on Product | Item is FL-DSH-01 |  | FL-DSH-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Proceed to Checkout | Atleast one item added to cart |  | Payment Details
| Step 8 | Enter Payment details and continue | Payment Card Data & Address |  | Please confirm the information below and then press continue.
| Step 9 | Click on Confirm |  |  | Thank you, your order has been submitted.
| Step 10 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 5 | Shopping Birds
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Birds
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Birds |  |  | Amazon Parrot
| Step 5 | Click on Product | Item is AV-CB-01 |  | AV-CB-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Proceed to Checkout | Atleast one item added to cart |  | Payment Details
| Step 8 | Enter Payment details and continue | Payment Card Data & Address |  | Please confirm the information below and then press continue.
| Step 9 | Click on Confirm |  |  | Thank you, your order has been submitted.
| Step 10 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 6 | Login & Logout
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Birds
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Sign out |  |  | Sign in
Web Application
| Scenario 7 | Add to cart
| Step # | Transaction Names | Test Data Required |  | Assertion
|  | Enter Landing Page URL | https://public.aspectran.com/ |  | Sample Apps
| Step 1 | Click on JPetStore Demo |  |  | Dog
| Step 2 | Cick on Sign in |  |  | Please enter your username and password.
| Step 3 | Enter Credentials and click Login | Valid Username and Password |  | My Account
| Step 4 | Click on Dog |  |  | Bulldog
| Step 5 | Click on Product | Item is K9-BD-01 |  | K9-BD-01
| Step 6 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 7 | Click on Reptiles |  |  | Rattlesnake
| Step 8 | Click on Product | Item is RP-SN-01 |  | RP-SN-01
| Step 9 | Click on Add to cart | Quantity must be random number |  | Shopping cart
| Step 10 | Click on Sign out |  |  | Sign in
API Call
| Scenario 8 | Search
| URL |  |  | Method | Test Data
| https://jpetstore.aspectran.com/catalog/searchProducts?keyword=fish |  |  | GET | Fish / Dog/ Cat / ...etc
AppServer | App01 | App02
WebServer | Web01 | Web02
SQL Server | SQL01
Firewall
Load Generators | LG1 | LG2
Smoke Test
Scenario 1
| 100% | 150% | 200%
Load Test | 100 Users / 1 Hr | 150 Users / 1 Hr | 200 Users / 1 Hr | Ramp up / Ramp down | 10 min |  |  |  | 4 min up / 6 min down
Soak Test | 40 Users / 8 Hr | 60 Users / 8 Hr | 80 Users / 8 Hr
Spike Test | 10 Users / 10 min
10 Users / 10 min
Scenario 2
Load Test
Soak Test
Spike Test
12000
| Response Time | Think Time | Pacing
API 1 | 1 Sec | 20 Sec | 10 Sec | 31
|  |  | 1 User in Hour | 116.129
|  |  | 10 Users | 1161.2903
|  |  | 100 Users | 11612.9032
| Transaction1 | Request 1
| Think Time | Think Time + Pacing
| Transaction2 | Pacing
Think Time
Transaction3
Think Time
Last Transaction
Pacing
Load Test Dates | Monday | Tuesday
Soak Test Dates | Monday | Tuesday | Wednesday
Spike Test Dates |  |  |  | Thursday | Friday

## Phase 4
Phase 4 | Configure Test Environment
1 | Use Production Environment | Backup production data | Isolate or disable 3rd party apps | Stubs
2 | Make an exact replica of production environment | create image of production machines to duplicate to test environment
3 | Replicate a customer environment
4 | Build a real environment from scratch
5 | Quick setup of test environment | Create a snapshot/image
6 | Isolating the test environment

## Phase 5
Phase 5 | Implementing Test Design
|  |  | Person assigned | Test Data |  | Integration Testing | Smoke Test
| Scenario 1 | Completed | @ET | username | password | Tested
| Scenario 2 | Completed | @ET |  |  | Tested
| Scenario 3 | Completed | @ET |  |  | Tested
| Scenario 4 | Completed | @ET |  |  | Tested
| Scenario 5 | Completed | @ET |  |  | Tested
| Scenario 6 | Completed | @ET |  |  | Tested
| Scenario 7 | Completed | @ET |  |  | Tested
| Scenario 8 | Completed | @ET |  |  | Tested
| Scenario 1 | Parameters
| Step 3 | Username,Password | EizaldinT,11413
| Step 6 | itemId | EST-1
|  | Correlation |  |  | 1. Add regular expression extractor
2. Replace the values
| Step 6 | itemId | EST-1

## Phase 6
Phase 6 | Execute Tests
Load Test
Run # 1
Response Time Table
Test Summary
| Field | Name | Value
| 1 | Total Test Duration | 2 hours
| 2 | Total Virtual Users | 200
| 3 | Total Requests Sent | 10000
| 4 | Environment | Pre-Prod
| 5 | Test Type | Load Test
| 6 | No of Execution | 1
Script 1: Login and Browse Products
| Transaction | Min Response Time (sec) | Max Response Time (sec) | Avg Response Time (sec) | Hits | Passed Transactions | Failed Transactions
| Login | 1.8 | 2.5 | 2.1 | 200 | 195 | 5
| Home Page | 0.9 | 1.7 | 1.2 | 400 | 390 | 10
| Category | 2.1 | 3.2 | 2.8 | 200 | 195 | 5
| Product | 2.5 | 4.3 | 3.2 | 100 | 95 | 5
| Logout | 1.7 | 3.5 | 2.5 | 100 | 95 | 5
Script 2: Search and Filter Products
| Transaction | Min Response Time (sec) | Max Response Time (sec) | Avg Response Time (sec) | Hits | Passed Transactions | Failed Transactions
| Search | 2.5 | 3.5 | 2.9 | 250 | 240 | 10
| Filter | 1.7 | 2.8 | 2.1 | 200 | 195 | 5
| Sort | 1.9 | 3.1 | 2.4 | 100 | 95 | 5
| View | 2.7 | 4.1 | 3.2 | 100 | 95 | 5
| Add to Cart | 2.2 | 3.7 | 2.8 | 100 | 95 | 5
Script 3: Checkout and Payment
| Transaction | Min Response Time (sec) | Max Response Time (sec) | Avg Response Time (sec) | Hits | Passed Transactions | Failed Transactions
| View Cart | 3.5 | 4.5 | 3.9 | 100 | 95 | 5
| Enter Checkout | 3.2 | 4.3 | 3.6 | 100 | 95 | 5
| Enter Payment | 4.5 | 5.8 | 5.2 | 150 | 135 | 15
| Submit Payment | 5.2 | 6.2 | 5.7 | 100 | 85 | 15
| Confirmation | 3.8 | 5.1 | 4.3 | 50 | 40 | 10
CPU, Memory, Network Table
| Metric | Server 1 | Server 2 | Server 3
| Minimum CPU Utilization | 10% | 15% | 12%
| Maximum CPU Utilization | 40% | 35% | 30%
| Average CPU Utilization | 20% | 25% | 20%
| Minimum Memory Utilization | 60% | 50% | 55%
| Maximum Memory Utilization | 80% | 70% | 75%
| Average Memory Utilization | 70% | 60% | 65%
| Minimum Network Utilization | 100 KB/s | 120 KB/s | 110 KB/s
| Maximum Network Utilization | 200 KB/s | 180 KB/s | 190 KB/s
| Average Network Utilization | 150 KB/s | 150 KB/s | 150 KB/s
Overal Analysis

## Phase 7
Phase 7 | Analyze, Report, Retest

## Notes
Load testing | jp@gc Ultimate Thread Group | 5 -10 minutes initial delay
Advantages: |  | Column | Description
| Flexible thread Scheduling: | Start Threads Count | Number of virtual users (threads) to start in that row.
| Dynamic Thread Control: | Initial Delay, sec | Time (in seconds) to wait before starting the threads in this row.
| Configurable Load Profile | Startup Time, sec | Time (in seconds) to ramp-up (gradually start) the threads.
| Easy to use | Hold Load For, sec | Duration (in seconds) to keep the threads running at full load.
|  | Shutdown Time, sec | Time (in seconds) to ramp-down (stop) the threads gradually.
Disadvantages:
| Resource Intensive | Example : Ultimate Thread Group
| Steep Learning curve | Start Threads Count | Initial Delay (sec) | Startup Time (sec) | Hold Load For (sec) | Shutdown Time (sec)
| Limited Report Options | 30 | 300 | 360 | 3600 | 180
Not suitable for all test scenarios
🕒 Initial Delay: 300 seconds (5 minutes)
→ No threads start during the first 5 minutes after the test begins.
🚀 Startup Time: 360 seconds (6 minutes)
→ 30 threads will ramp up gradually over the next 6 minutes.
→ That's about 1 new thread every 12 seconds.
📈 Hold Load For: 3600 seconds (1 hour)
→ Once all 30 threads are started, they will keep running at full load for 1 hour.
🛑 Shutdown Time: 180 seconds (3 minutes)
→ After 1 hour of holding load, the 30 threads will ramp down (stop) gradually over 3 minutes.
Example: Open Model Thread Group
|  | Pause | Rate | Pause | Comment
|  | 0 | 10 | 60 | Ramp-up phase
|  | 0 | 50 | 30 | Load spike
|  | 0 | 5 | 120 | Recovery phase
|  | Field | Meaning
|  | Pause (Before) | How long to wait before starting this step (in seconds).
|  | Rate | User arrival rate (users/sec) during this step.
|  | Pause (After) | How long this rate should continue (in seconds).
|  | Comment | A label to describe the purpose of this step (for readability only).
⏸ Wait 0s → 🔼 Ramp up with 10 users/sec for 60s
⏸ Then 0s pause → 🚀 Spike to 50 users/sec for 30s
⏸ Then 0s pause → 🔽 Drop to 5 users/sec for 120s
Example: Arrival Thread Group
|  | Start Users/Sec | End Users/Sec | Ramp-Up Time (sec) | Hold Target Rate Time | Comment
|  | 5 | 20 | 60 | 120 | Ramp and Hold Test
Arrival rate -> 10 sec
Execution time -> Hold Target Time -> 60 sec (1 min)
10*60 = 600
Example: Concurrency Thread Group
|  | Field | Value
|  | Target Concurrency | 50
|  | Ramp-Up Time (sec) | 60
|  | Hold Target Rate Time | 180
|  | Iterations Limit | empty (infinite) or set a value like 5
|  | Comment | "50 users stable load"
|  | User Load | 100 Users
|  | Duration (Steady State) | 60 min
|  | Ramp up Time | 6 min
|  | Ramp up Step | 2025-06-05
|  | Field | Name | Explanation
|  | 1 | Target Concurrency | Number of concurrent users (threads) to maintain at all times
|  | 2 | Ramp-Up Time (sec) | Time to gradually reach the target concurrency level
|  | 3 | Hold Target Rate Time (sec) | Time to keep the target concurrency stable once reached
|  | 4 | Iterations Limit | (Optional) Max number of iterations per thread before it stops
|  | 5 | Comment | Any label or description for your test step
|  | Stress Test - CLI | jmeter -n -t Stress-Testing-and-RegExpression.jmx -l Stress-Testing-and-RegExpression.jtl -Jthreads=1000 -JrampUp=600
WARN StatusConsoleListener The use of package scanning to locate plugins is deprecated and will be removed in a future release
WARN StatusConsoleListener The use of package scanning to locate plugins is deprecated and will be removed in a future release
WARN StatusConsoleListener The use of package scanning to locate plugins is deprecated and will be removed in a future release
WARN StatusConsoleListener The use of package scanning to locate plugins is deprecated and will be removed in a future release
Creating summariser <summary>
Created the tree successfully using Stress-Testing-and-RegExpression.jmx
Starting standalone test @ 2025 May 3 21:05:20 EET (1746299120991)
Waiting for possible Shutdown/StopTestNow/HeapDump/ThreadDump message on port 4445
summary + 46 in 00:00:09 = 5.3/s Avg: 237 Min: 0 Max: 493 Err: 0 (0.00%) Active: 2 Started: 2 Finished: 0
summary + 559 in 00:00:30 = 18.6/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%) Active: 7 Started: 7 Finished: 0
summary = 605 in 00:00:39 = 15.7/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 1223 in 00:00:30 = 40.8/s Avg: 230 Min: 0 Max: 498 Err: 0 (0.00%) Active: 12 Started: 12 Finished: 0
summary = 1828 in 00:01:09 = 26.6/s Avg: 232 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 1820 in 00:00:30 = 60.7/s Avg: 236 Min: 0 Max: 502 Err: 0 (0.00%) Active: 17 Started: 17 Finished: 0
summary = 3648 in 00:01:39 = 37.0/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 2470 in 00:00:30 = 82.4/s Avg: 235 Min: 0 Max: 501 Err: 0 (0.00%) Active: 22 Started: 22 Finished: 0
summary = 6118 in 00:02:09 = 47.6/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 3107 in 00:00:30 = 103.6/s Avg: 235 Min: 0 Max: 501 Err: 0 (0.00%) Active: 27 Started: 27 Finished: 0
summary = 9225 in 00:02:39 = 58.2/s Avg: 235 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 3748 in 00:00:30 = 124.8/s Avg: 235 Min: 0 Max: 502 Err: 0 (0.00%) Active: 32 Started: 32 Finished: 0
summary = 12973 in 00:03:09 = 68.8/s Avg: 235 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 4403 in 00:00:30 = 146.9/s Avg: 234 Min: 0 Max: 501 Err: 0 (0.00%) Active: 37 Started: 37 Finished: 0
summary = 17376 in 00:03:39 = 79.5/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 5052 in 00:00:30 = 168.3/s Avg: 233 Min: 0 Max: 502 Err: 0 (0.00%) Active: 42 Started: 42 Finished: 0
summary = 22428 in 00:04:09 = 90.2/s Avg: 234 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 5608 in 00:00:30 = 187.0/s Avg: 237 Min: 0 Max: 502 Err: 0 (0.00%) Active: 47 Started: 47 Finished: 0
summary = 28036 in 00:04:39 = 100.6/s Avg: 235 Min: 0 Max: 502 Err: 0 (0.00%)
summary + 6280 in 00:00:30 = 209.3/s Avg: 235 Min: 0 Max: 503 Err: 0 (0.00%) Active: 52 Started: 52 Finished: 0
summary = 34316 in 00:05:09 = 111.2/s Avg: 235 Min: 0 Max: 503 Err: 0 (0.00%)
summary + 6926 in 00:00:30 = 230.9/s Avg: 235 Min: 0 Max: 501 Err: 0 (0.00%) Active: 57 Started: 57 Finished: 0
summary = 41242 in 00:05:39 = 121.8/s Avg: 235 Min: 0 Max: 503 Err: 0 (0.00%)
Create HTML Report
|  | 1 | Have Your jmeter Script ready
|  | 2 | Add simple data writer listener to the test plan
|  | 3 | Create a csv extension file and add it as a file for simple data writer
|  | 4 | Configure the setting, select all except "save as XML"
|  | 5 | Execute test
|  | 6 | Click tools -> Generate HTML report